## Project 1
Project 1: Telco Churn Model | [9 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Kick off | [7 empty] | COMPANY NAME | [6 empty] | Point Estimation Ltd.
PROJECT MANAGER |  | Sourav Das | [7 empty] | DATE | [6 empty] | 2021-08-29
Current Week ➜
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | COMMENTS | PRIORITY | PCT OF TASK COMPLETE | STATUS | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28
[10 empty] | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Stakeholder Brief
1.1 | Meeting with stakeholder, Requirement gathering | SK | 2021-06-01 | 2021-06-01 12:00 | 0.5 | Ongoing |  | 100% | Complete
1.2 | Ask about more information regarding data attributes from stakeholder | SK | 2021-06-02 | 2021-06-07 | 5 |  |  | 100% | Complete
| Data Understanding |  | 2021-06-01 | 2021-06-06 | 5
2.1 | view and get understanding of both datasets provided by stakeholder | SK | 2021-06-01 | 2021-06-06 | 5 |  |  | 100% | Complete
2.2 | Get overview of relevant attributes (identification of variables) | SK | 2021-06-01 | 2021-06-03 | 2 |  |  | 100% | Complete
2.3 | Research and create data dictionary | SK | 2021-06-01 | 2021-06-02 | 1 |  |  | 100% | Complete
| Data Preparation & Modelling |  | 2021-06-07 | 2021-06-20 | 13
3.1 | Exploratory Data Analysis | SK | 2021-06-07 | 2021-06-12 | 5 |  |  | 100% | Complete
3.2 | Data Transformation | SK | 2021-06-12 | 2021-06-13 | 1 |  |  | 100% | Complete
3.3 | Feature Selection | SK | 2021-06-09 | 2021-06-14 | 5 |  |  | 100% | Complete
3.4 | Run the Models | SK | 2021-06-15 | 2021-06-18 | 3 |  |  | 100% | Complete
3.5 | Evaluation of Models | SK | 2021-06-19 | 2021-06-20 | 1 |  |  | 100% | Complete
3.6 | Tuning the model: (Hyper parameter) | SK | 2021-06-19 | 2021-06-20 | 1 |  |  | 100% | Complete
| Generate Insights |  | 2021-06-21 | 2021-06-24 | 3
4.1 | Generate some insights and stats valuable for the clients | SK | 2021-06-21 | 2021-06-23 | 2 |  |  | 100% | Complete
4.2 | Some insightful visualisations of the data | SK | 2021-06-21 | 2021-06-23 | 2 |  |  | 100% | Complete
4.3 | Sharing initial insights with the client | SK | 2021-06-21 | 2021-06-22 | 1 |  |  | 100% | Complete
4.4 | Tackle the misclassification cost problem | SK | 2021-06-21 | 2021-06-24 | 3 |  |  | 100% | Complete
| Create Presentation |  | 2021-07-03 | 2021-07-08 | 5
5.1 | Prepare/Populate the presentation planner | SK | 2021-06-03 | 2021-06-05 | 2 |  |  | 100% | Complete
5.2 | Create a draft presentation | SK | 2021-07-06 | 2021-07-09 | 3 |  |  | 100% | Complete
5.3 | Share it with the Manager | SK | 2021-07-07 | 2021-07-09 | 2 |  |  | 100% | Complete
5.4 | De-brief | SK | 2021-07-10 | 2021-07-11 | 1 |  |  | 100% | Complete